## Sheet1
% Complete | Task Name | Comments | Start | Finish | Duration | Predecessors | Resource Names
44% | SBSA Viya4 Production Deployment |  | Mon 9/12/22 | Thu 11/24/22 | 53.35 days
0% | Initiation |  | Mon 9/12/22 | Mon 9/19/22 | 5 days
100% | Confirm Project Scope |  | Mon 9/19/22 | Mon 9/19/22 | 0 days |  | SAS Project Manager[0%]
100% | Support Contracts to be signed (Verbally agreed) |  | Mon 9/12/22 | Tue 9/13/22 | 0 days | 3 | SAS Project Manager[0%]
100% | Resource On-Boarding |  | Tue 9/13/22 | Tue 9/13/22 | 0 days | 4 | SAS Project Manager[0%]
95% | System Access |  | Mon 9/19/22 | Mon 9/19/22 | 0 days | 5 | SAS Project Manager[0%]
20% | Account and Project Management |  | Mon 9/19/22 | Wed 10/19/22 | 23 days
20% | Project Management |  | Mon 9/19/22 | Wed 10/19/22 | 23 days |  | SAS Project Manager[25%]
86% | Architecture |  | Wed 9/21/22 | Wed 10/19/22 | 21 days
100% | Architecture Workshops |  | Wed 9/21/22 | Fri 9/30/22 | 7.25 days
100% | Architecture Workshop 1 - Infrastructure & Storage |  | Wed 9/21/22 | Wed 9/21/22 | 0.25 days |  | SAS Technical Architect[25%],SAS Technical Team Lead[25%]
100% | Architecture Workshop 2 - Security Requirements |  | Thu 9/29/22 | Thu 9/29/22 | 0.25 days | 11 | SAS Technical Architect[25%],SAS Technical Team Lead[25%]
100% | Architecture Workshop 3 - Deployment Topology |  | Fri 9/30/22 | Fri 9/30/22 | 0.25 days | 12
100% | Architecture Workshop 4 - General |  | Fri 9/30/22 | Fri 9/30/22 | 0.25 days | 13
100% | Architecture Workshop 5 - General |  | Fri 9/30/22 | Fri 9/30/22 | 0.25 days | 14
100% | Architecture Workshop 6 - General |  | Fri 9/30/22 | Fri 9/30/22 | 0.25 days | 15
95% | Technical Arhitecture Document | Dependant on the Multi-Domain and Final storage NetApps | Mon 10/10/22 | Mon 10/17/22 | 6 days | 16 | SAS Technical Architect,SAS Technical Team Lead[25%]
100% | Document Review and Signoff |  | Mon 10/17/22 | Mon 10/17/22 | 1 day | 17 | SAS Technical Architect[25%]
0% | Review Plan - Outcome of Architecture workshops |  | Wed 10/19/22 | Wed 10/19/22 | 1 day |  | SAS Technical Architect[25%],SAS Technical Team Lead[25%]
75% | Azure Infrastructure and pre-requisites | Refer to Appendix A in the Architecture Document | Wed 10/19/22 | Mon 11/7/22 | 13 days
70% | Provision Azure Kubernetes Service (AKS) |  | Wed 10/19/22 | Fri 11/4/22 | 12 days | 19 | SBSA Architect,Microsoft Specialist
100% | Azure Container Registry (ACR) |  | Wed 10/19/22 | Mon 10/24/22 | 3 days | 19 | SBSA Architect,Microsoft Specialist
100% | Kubernetes Accounts |  | Wed 10/19/22 | Mon 10/24/22 | 3 days | 19 | SBSA Architect,Microsoft Specialist
100% | Install client tools, Azure CLI, Helm, Kustomize |  | Fri 10/28/22 | Fri 10/28/22 | 1 day | 19 | SBSA Architect,Microsoft Specialist
0% | Install Ingress Controller |  | Mon 11/7/22 | Mon 11/7/22 | 0.5 days | 19,21 | SBSA Architect,Microsoft Specialist
0% | Environment validation |  | Mon 11/7/22 | Mon 11/7/22 | 1 day | 19,21 | SBSA Architect,Microsoft Specialist,SAS Deployment Specialist
60% | Pre-Installation Tasks |  | Mon 10/31/22 | Mon 11/7/22 | 5.6 days
100% | Generate Certificates |  | Mon 10/31/22 | Mon 10/31/22 | 0.2 days | 24 | SBSA Architect,Microsoft Specialist
0% | Review release documentation |  | Mon 10/31/22 | Mon 10/31/22 | 0.2 days | 28 | SAS Deployment Specialist
100% | Install Mirror Manager |  | Mon 10/31/22 | Mon 10/31/22 | 0.2 days | 29 | SAS Deployment Specialist
100% | Create Mirror Registry |  | Mon 10/31/22 | Mon 10/31/22 | 0.2 days | 30 | SAS Deployment Specialist
100% | Download Deployment Assets |  | Mon 10/31/22 | Mon 10/31/22 | 0.2 days | 31 | SAS Deployment Specialist
100% | Download License and Certificates |  | Tue 11/1/22 | Tue 11/1/22 | 0.2 days | 32 | SAS Deployment Specialist
100% | Create Deployment Directory Structure |  | Tue 11/1/22 | Tue 11/1/22 | 0.2 days | 33 | SAS Deployment Specialist
0% | Create RWX Storage Class (Azure Files/NetApp) |  | Mon 11/7/22 | Mon 11/7/22 | 0.2 days | 34,21 | SAS Deployment Specialist
0% | Test PVC Creation |  | Mon 11/7/22 | Mon 11/7/22 | 0.2 days | 35 | SAS Deployment Specialist
0% | Deploy the SAS Viya Deployment Operator |  | Mon 11/7/22 | Mon 11/7/22 | 0.2 days | 36 | SAS Deployment Specialist
7% | Installation Tasks |  | Mon 11/7/22 | Thu 11/10/22 | 3 days
0% | Create kustomization file |  | Mon 11/7/22 | Tue 11/8/22 | 0.5 days | 37 | SAS Deployment Specialist
11% | Add required customizations |  | Tue 11/8/22 | Wed 11/9/22 | 1.9 days
100% | Mirror Registry |  | Tue 11/8/22 | Tue 11/8/22 | 0.2 days | 39 | SAS Deployment Specialist
0% | Update Checker |  | Tue 11/8/22 | Tue 11/8/22 | 0.2 days | 41 | SAS Deployment Specialist
0% | Site Default File |  | Tue 11/8/22 | Tue 11/8/22 | 0.15 days | 42 | SAS Deployment Specialist
0% | TLS Configuration |  | Tue 11/8/22 | Tue 11/8/22 | 0.15 days | 43 | SAS Deployment Specialist
0% | PostgreSQL Configuration |  | Tue 11/8/22 | Tue 11/8/22 | 0.15 days | 44 | SAS Deployment Specialist
0% | Open Distro for Elasticsearch |  | Tue 11/8/22 | Wed 11/9/22 | 0.15 days | 45 | SAS Deployment Specialist
0% | MPP CAS Configuration |  | Wed 11/9/22 | Wed 11/9/22 | 0.15 days | 46 | SAS Deployment Specialist
0% | Configure CAS Settings |  | Wed 11/9/22 | Wed 11/9/22 | 0.15 days | 47 | SAS Deployment Specialist
0% | Configure SAS/Connect Settings |  | Wed 11/9/22 | Wed 11/9/22 | 0.15 days | 48 | SAS Deployment Specialist
0% | Set Default Locale and Encoding |  | Wed 11/9/22 | Wed 11/9/22 | 0.15 days | 49 | SAS Deployment Specialist
0% | Specify PVC to use RWX storage class |  | Wed 11/9/22 | Wed 11/9/22 | 0.15 days | 50 | SAS Deployment Specialist
0% | Configure SAS/Access to Synapse |  | Wed 11/9/22 | Wed 11/9/22 | 0.15 days | 51 | SAS Deployment Specialist
0% | Install and Configure Open Source (Python) |  | Thu 11/10/22 | Thu 11/10/22 | 0.15 days | 52 | SAS Deployment Specialist
0% | Install SAS Orchestration Tool |  | Thu 11/10/22 | Thu 11/10/22 | 0.15 days | 53 | SAS Deployment Specialist
0% | Create the SAS Deployment Custom Resource |  | Thu 11/10/22 | Thu 11/10/22 | 0.15 days | 54 | SAS Deployment Specialist
0% | Deploy Software (Manual or Automatic) |  | Thu 11/10/22 | Thu 11/10/22 | 0.15 days | 55 | SAS Deployment Specialist
0% | Logging and Monitoring |  | Thu 11/10/22 | Fri 11/11/22 | 1 day
0% | Clone v4m project |  | Thu 11/10/22 | Thu 11/10/22 | 0.25 days | 56 | SAS Deployment Specialist
0% | Mirror Images |  | Thu 11/10/22 | Fri 11/11/22 | 0.25 days | 58 | SAS Deployment Specialist
0% | Install Monitoring |  | Fri 11/11/22 | Fri 11/11/22 | 0.25 days | 59 | SAS Deployment Specialist
0% | Install Logging |  | Fri 11/11/22 | Fri 11/11/22 | 0.25 days | 60 | SAS Deployment Specialist
0% | Post Installation Tasks |  | Fri 11/11/22 | Wed 11/16/22 | 3 days
0% | Configure Identities |  | Fri 11/11/22 | Fri 11/11/22 | 0.2 days | 61 | SAS Deployment Specialist
0% | Configure mail server connection |  | Fri 11/11/22 | Fri 11/11/22 | 0.2 days | 63 | SAS Deployment Specialist
0% | Configure AD SSO |  | Mon 11/14/22 | Mon 11/14/22 | 0.2 days | 64 | SAS Deployment Specialist
0% | Configure Monitoring and Logging |  | Mon 11/14/22 | Mon 11/14/22 | 0.2 days | 65 | SAS Deployment Specialist
0% | Configure CAS binary port |  | Mon 11/14/22 | Mon 11/14/22 | 0.2 days | 66 | SAS Deployment Specialist
0% | Configure CAS disk cache / saswork |  | Mon 11/14/22 | Mon 11/14/22 | 0.2 days | 67 | SAS Deployment Specialist
0% | Conigure Data Access (ADLS & Synapse) |  | Mon 11/14/22 | Mon 11/14/22 | 0.15 days | 68 | SAS Deployment Specialist
0% | Configure Model Access |  | Mon 11/14/22 | Tue 11/15/22 | 0.15 days | 69 | SAS Deployment Specialist
0% | Configure SAS Data Quality |  | Tue 11/15/22 | Tue 11/15/22 | 0.15 days | 70 | SAS Deployment Specialist
0% | Configure SAS for Microsoft 365 |  | Tue 11/15/22 | Tue 11/15/22 | 0.15 days | 71 | SAS Deployment Specialist
0% | Configure SAS Intelligent Decisioning |  | Tue 11/15/22 | Tue 11/15/22 | 0.15 days | 72 | SAS Deployment Specialist
0% | Configure SAS Model Manager |  | Tue 11/15/22 | Tue 11/15/22 | 0.15 days | 73 | SAS Deployment Specialist
0% | Configure Python Support (3.6 + Supporting Modules |  | Tue 11/15/22 | Tue 11/15/22 | 0.15 days | 74 | SAS Deployment Specialist
0% | Configure Risk Modeling |  | Tue 11/15/22 | Tue 11/15/22 | 0.15 days | 75 | SAS Deployment Specialist
0% | Configure Visual Data Science |  | Wed 11/16/22 | Wed 11/16/22 | 0.15 days | 76 | SAS Deployment Specialist
0% | Configure SAS Visual Analytics |  | Wed 11/16/22 | Wed 11/16/22 | 0.15 days | 77 | SAS Deployment Specialist
0% | Configure SAS Visual Machine Learning |  | Wed 11/16/22 | Wed 11/16/22 | 0.15 days | 78 | SAS Deployment Specialist
0% | Configure SAS Visual Statistics |  | Wed 11/16/22 | Wed 11/16/22 | 0.15 days | 79 | SAS Deployment Specialist
0% | Deployment Validation |  | Wed 11/16/22 | Wed 11/23/22 | 5 days
0% | Run the SAS Viya Deployment Report |  | Wed 11/16/22 | Thu 11/17/22 | 0.5 days | 80 | SAS Deployment Specialist,SBSA Architect
0% | Validate SAS Environment Manager |  | Thu 11/17/22 | Thu 11/17/22 | 0.5 days | 82 | SAS Deployment Specialist,SBSA Architect
0% | Validate SAS Studio |  | Thu 11/17/22 | Fri 11/18/22 | 0.5 days | 83 | SAS Deployment Specialist,SBSA Architect
0% | Validate Data Access (ADLS2 & Synapse) |  | Fri 11/18/22 | Fri 11/18/22 | 0.5 days | 84 | SAS Deployment Specialist,SBSA Architect
0% | Validate CAS Connectivity |  | Fri 11/18/22 | Mon 11/21/22 | 0.5 days | 85 | SAS Deployment Specialist,SBSA Architect
0% | Validate SAS Visual Analytics |  | Mon 11/21/22 | Mon 11/21/22 | 0.5 days | 86 | SAS Deployment Specialist,SBSA Architect
0% | Validate SAS Visual Statistics |  | Mon 11/21/22 | Tue 11/22/22 | 0.5 days | 87 | SAS Deployment Specialist,SBSA Architect
0% | Validate SAS Visual Machine Learning |  | Tue 11/22/22 | Tue 11/22/22 | 0.5 days | 88 | SAS Deployment Specialist,SBSA Architect
0% | Validate SAS Model Manager |  | Tue 11/22/22 | Wed 11/23/22 | 0.5 days | 89 | SAS Deployment Specialist,SBSA Architect
0% | Compile Validation Document |  | Wed 11/23/22 | Wed 11/23/22 | 0.5 days | 90 | SAS Deployment Specialist,SBSA Architect
0% | Implementation Close Out |  | Wed 11/23/22 | Wed 11/23/22 | 0.25 days
0% | Envrionment Handover and Sign-off |  | Wed 11/23/22 | Wed 11/23/22 | 0.25 days | 91 | SBSA Project Sponsor,SBSA Architect,SAS Deployment Specialist
0% | Data Services Testing |  | Wed 11/23/22 | Thu 11/24/22 | 0.5 days | 93